## Sheet1
CSC 441 Kanban Board
Backlog | Ready | Coding and Unit Testing | Testing and Integration | Submitted | Done
Each username shall have a single ToDo list instance made up of zero or more ToDoItem instances. |  |  |  | Built Server-side validation for the To-do list form using Node.js. Validation based off of project description guidelines. Est. Hrs: 4 Act Hrs: 10 | Built a main navigation page that serves as the homepage for the site. Est. Hrs: 1 Act. Hrs: .5
A ToDo list is uniquly identified using an integer value automatically generated by the database. |  |  |  | Built basic server for webpage interactions using Node.js. Server responds only to requests from the to-do form page Est. Hrs: 5 Act Hrs: 2 | Built a form for the to-do list items. Form is housed on individual page for easy access and has no validation Est. Hrs: 1 Act. Hrs: .5
To-Do list has a username value. Each username value must be unique and must contain at least one upper or lower-case letter. Only upper and lower-case letters and the space character are allowed in a username. |  |  |  | User can create a new item in a to-do list. A new to-do list item is created when all of its data values are valid Est. Hrs: 3 Act. Hrs: 1.5 | Built CSS file for formatting. This file holds formatting for all webpages Est. Hrs: 5 Act. Hrs: 2
A to-do item is uniquely identified using the ToDo id value (a foreign key field) along with an integer value automatically generated by the database. |  |  |  | Connected Node.js server to MySQL database for todo Items Est. Hrs: .5 Act Hrs. .25 | Various Code edits for design and aesthetics Est. Hrs: 10 Act. Hrs:
To-do item must have a dateCreated. This value is created by the system instead of the user |  |  |  | Added code to Node.js server to add new to-do items to database following validation Est. Hrs: .5 Act Hrs. .25 | Added menu bar for easy navigation. Edited main CSS file in order to unify changes across the website Est. Hrs: 1 Act. Hrs: .5
To-do item must have a description. This value describes the to-do item and must contain at least one character. |  |  |  | Added code to Node.js server to display page and error upon failure to add to database Est. Hrs: .5 Act Hrs. .25 | User can display all items in a to-do list. The user may request display of the to-do items using any of the following: i) dateCreated - from oldest to newest. ii) description - in alphabetical order. iii) priority - from highest to lowest. iv) dueDate - in alphabetical order. v) status - in alphabetical order. Individual pages were built for each of these sorted options. Data has been hardcoded for the time being. Est. Hrs: 4 Act. Hrs: 2
To-do item may have a priority. The priority value, if included by the user, must be a digit (1 through 9) or an uppercase letter (A through Z). Using digits, a priority of 1 is highest and 9 is lowest. Using characters, a priority of A is highest and Z is lowest. When a person uses both digits and uppercase letters, the digits have a higher priority |  |  |  | Added server side code to return the styling CSS document upon request Est. Hrs: 1 Act Hrs. .5 | Verify data to ensure that invalid values are not added on clientside javascript. Verifies based on project requirements for all elements Est. Hrs: 3 Act. Hrs: 2
To-do item may have a dueDate. The dueDate value, if included by the user, may be a valid date or any nonempty text value. Examples of text values are: today, tomorrow, and next week.
To-do item may have a status. The status value, if included by the user, must be one of the following: i) not-started ii) in-progress iii) done
Users can create as many username values as they wish. Each username has its own to-do list items
User can update an existing item in a to-do list. An existing to-do list item is updated when all of the changed data values are valid.
User can remove an existing item in a to-do list. Any existing to-do list item may be deleted.